## Slide 1: PRESANTATION BY: Labanya Saha(21201059) Mehadi Islam(21201065) Saummon Jannat(21201066) Paria Chowdhury(21201067)
SIGN LANGUAGE

## Slide 2
PROJECT SCHEDULING(CPM)
Activity No | ACTIVITY | DURATION | PRECENING ACTIVITY
A | Project Initiation | 3 | ----------
B | Requirement Gatherings | 3 | A
C | System Design | 6 | B
D | Development | 10 | C
E | Testing | 6 | D
F | Documentation | 5 | D
G | Deploment | 2 | E
H | Post-Development Support | 4 | F

## Slide 3
B
AAA
B
A
F
C
D
E
H
G
3 6
3 3 6
0 3
0 3 3
6 12
6 6 12
12 22
12 10 22
22 28
23 6 29
22 27
22
5 27
28 30
29 2 31
27 31
27 4 31

## Slide 4
FORWARD,BACKWARD PASS & CRITICAL PATH CALCULATION
ACTIVITY NO | ACTIVITY | DURATION(WEEK) | PRECEDING ACTIVITY | ES | EF | LS | LF | SLACK | CRITICAL PATH OR NOT
A | Project initation | 3 | ------- | 0 | 3 | 0 | 3 | 0 | YES
B | Requirements gathering | 3 | A | 3 | 6 | 3 | 6 | 0 | YES
C | System design | 6 | B | 6 | 12 | 6 | 12 | 0 | YES
D | Development | 10 | C | 12 | 22 | 12 | 22 | 0 | YES
E | Testing | 6 | D | 22 | 28 | 23 | 29 | 1 | NO
F | Documentation | 5 | D | 22 | 27 | 22 | 27 | 0 | YES
G | Deployment | 2 | E | 28 | 30 | 29 | 31 | 2 | NO
H | Post Deployment Support | 4 | F | 27 | 31 | 27 | 31 | 0 | YES